## LOG
Chess Project Log
Task | Feature | Status | Duration | Description | Comments
Extract windows form chess logic to a new, refactored class based chess library that can be used for any C# based project | Game, Board, Player, and Pieces (mostly setting up key components) | Completed on Mar 25 | ~4 hours - Implement Pieces ('Piece' is abstract class, 'Pawn', 'Rook', 'Queen', etc are derived classes, Created 'Game' class that takes parameters 'board', 'p1', 'p2', create 'Board' and 'Player' classes, remove unnessesary / redundant code | To begin this project, I am taking my existing windows form chess logic and creating a universal c# chess library that is stored in a dedicated class library. I am using existing logic to speed up the process. | What I plan to do with the new and improved chess project, is make it move expandable and allow for more features such as an AI player, TCP/IP muliplayer, and many more.
Refactor 'GetMoves()' method for each piece | Change the 'Get Moves' abstract method so it is much more simplified | Completed Mar 26 | ~2 hours - Find a new structure to generate my pieces moves. It ended up being extremely more efficient than before where I had tons of if statements to find the moves. | The technique I used was to give each piece a template. The template defined what directions were valid for the specific piece. Ex. Pawn's template was 1 forward, King would be 1 in all directions. Also you would define a range. In my case, the kings, knights, and pawns range would be 1, and queen, bishop and rook would have a range of the size of the board. | The image to the right is a screenshot of how the queen class looks, the layout is similar for all other piece classes, you can see that the templates define the direction on the plane of a 2d array (which is the chessboard). Below there is a method held in a different utility class that takes the board, current piece, range, and templates to return a list of moves on the board.

## EXAMPLE
PROG280 Final Project Log - EXAMPLE
Task | Feature | Status | Duration | Description | Comments
Implement transparent image support | Chat | Completed | 30 minutes | Wasn't that hard I found an example on codeproject | 10/10 would not do this again
Add emoji support | Chat | Abandonned | 5 hours | No one even likes emojis | This is a debatable topic but I decided to scrap the feature
Additional TCP connection for sharing screen image | Meeting | In-Progress | ~1 hour so far | An additional connection will be created so the images do not disrupt the chat functionality | Works okay but UDP may have alleviated bandwidth issues
Request control | Remote Control | Not-Started |  | Allow a user to request control from the host PC | Struggling on where to begin this task